## BackLog
App | Feature ID | Feature Rank | Topic | Sub Topic | Type | Name | Description | Status | Role | Estimated Effort (hours) | Story Points | Priority | Reference | Complete
Brain Food App | 1 | 1 | Feature | Feature | User Story | Web application | As a User I should be able to open the app, see my location and at least 4 Food trucks within an x-mile radius | In Review | Product Owner | 0 | 10 | High | Project #
Brain Food App | 1 | 1 | Feature | Infrastructure | Setup | Azure Table | Create Azure Table Structure to store Food Truck Data Schema | New | Scrum Master | 1 |  | High | Doc URL link…
Brain Food App | 1 | 1 | Feature | Infrastructure | Setup | AppService | Create Azure App Service to Host WEBAPI and Web Application | New | Scrum Master | 1 |  | High
Brain Food App | 1 | 1 | Feature | Development | Coding | Data Source | Consume Food Truck Data Source on a daily basis every morning and store in Database. Data is always replaced with most recent. | New | Scrum Master | 3 |  | High
Brain Food App | 1 | 1 | Feature | Development | Coding | WebAPI | Develop WebAPI to expose Food Truck data in a View Model for given parameter location and optional parameter of radius in miles | New | Scrum Master | 8 |  | High
Brain Food App | 1 | 1 | Feature | Development | Coding | Web application dev | Develop SPA Web application to request food truck data from WebAPI based on a users location and present results on a Map | New | Scrum Master | 8 |  | High
Brain Food App | 2 | 2 | Feature | Feature | User Story | User interaction | As a User I should be to click on the Map Food Truck Icon to learn more about it (Name, Description, Opening Times, Link to External URL) | New | Product Owner | 0 | 2 | Medium
Brain Food App | 2 | 2 | Feature | Development | Coding | Map enhancement | Develop Map interaction to present details of a Map point to the user. | New | Scrum Master | 3 |  | Medium
Brain Food App | 3 | 3 | Feature | Feature | User Story | User input - location | As a User I should be able to manually enter a location to see what Food trucks are available in that area | New | Product Owner | 0 | 1 | Medium
Brain Food App | 3 | 3 | Feature | Development | Coding | Web app enhancement - location input | Enhance the web application to allow a manual input of a San Francisco Location and submit for results | New | Product Owner | 8 |  | Medium
Brain Food App | 4 | 4 | Feature | Feature | User Story | Search Terms | As a User I should be able to type in a search term (Such as food type) and see a list of Food Trucks associated with that search result | New | Product Owner | 0 | 1 | Low
Brain Food App | 4 | 4 | Feature | Development | Coding | WEBAPI enhancement - search terms | Enhance the WEBAPI to create a new Search Endpoint where a user can submit a text search against the Food Truck Data and return a list of Food Truck details | New | Scrum Master | 3 |  | Low
Brain Food App | 4 | 4 | Feature | Development | Coding | Web application enhancement - search terms | Enhance to web application to allow manual input of a search term, and present the results in a list. | New | Scrum Master | 6 |  | Low
Brain Food App | 5 | 5 | Testing | Testing | Coding | Develope Test Cases | Prepare Automated Tests | New | Scrum Master | 16 |  | High

## Pivot View
App | Brain Food App
Row Labels | Sum of Estimated Effort (hours)
1 | 21
1 | 21
Feature | 21
Development | 19
Data Source | 3
Consume Food Truck Data Source on a daily basis every morning and store in Database. Data is always replaced with most recent. | 3
Web application dev | 8
Develop SPA Web application to request food truck data from WebAPI based on a users location and present results on a Map | 8
WebAPI | 8
Develop WebAPI to expose Food Truck data in a View Model for given parameter location and optional parameter of radius in miles | 8
Feature | 0
Web application | 0
As a User I should be able to open the app, see my location and at least 4 Food trucks within an x-mile radius | 0
Infrastructure | 2
AppService | 1
Create Azure App Service to Host WEBAPI and Web Application | 1
Azure Table | 1
Create Azure Table Structure to store Food Truck Data Schema | 1
2 | 3
2 | 3
Feature | 3
Development | 3
Map enhancement | 3
Develop Map interaction to present details of a Map point to the user. | 3
Feature | 0
User interaction | 0
As a User I should be to click on the Map Food Truck Icon to learn more about it (Name, Description, Opening Times, Link to External URL) | 0
3 | 8
3 | 8
Feature | 8
Development | 8
Web app enhancement - location input | 8
Enhance the web application to allow a manual input of a San Francisco Location and submit for results | 8
Feature | 0
User input - location | 0
As a User I should be able to manually enter a location to see what Food trucks are available in that area | 0
4 | 9
4 | 9
Feature | 9
Development | 9
Web application enhancement - search terms | 6
Enhance to web application to allow manual input of a search term, and present the results in a list. | 6
WEBAPI enhancement - search terms | 3
Enhance the WEBAPI to create a new Search Endpoint where a user can submit a text search against the Food Truck Data and return a list of Food Truck details | 3
Feature | 0
Search Terms | 0
As a User I should be able to type in a search term (Such as food type) and see a list of Food Trucks associated with that search result | 0
5 | 16
5 | 16
Testing | 16
Testing | 16
Develope Test Cases | 16
Prepare Automated Tests | 16
Grand Total | 57

## Misc (hidden)
Topic | Role | Status | Priority
Feature | User | New | Low
Testing | Product Owner | Assigned | Medium
Infrastructure | Scrum Master | Parked | High
Documentation |  | In Review | Urgent
Bug |  | UnAssigned
Development